## Revenue Drivers
Retain and Grow Revenue from Existing Clients | Upsell Additional Services to Existing Clients | New Revenue: Acquire New Clients
Week 1-52 | Week 1-52 | Week 1-52
1. Schedule and conduct a meeting with key stakeholders from existing clients. | 1. Identify potential upsell opportunities for each client. | 1. dentify and qualify new sales leads.
Success Metric: 1 meeting conducted per week. | Success Metric: List of upsell opportunities for each client. | Success Metric: 4 sales-qualified leads (SQLs) identified per week.
Timeline: Every week. | Timeline: Week 1 of each month. | Timeline: Every week.
2. Document feedback and action items from meetings. | 2. Schedule and conduct a meeting with stakeholders to discuss upsell options.
Success Metric: Documented meeting minutes and follow-up actions. | Success Metric: 1 upsell meeting conducted per month. | Bi-Weekly Activities:
Timeline: Every week. | Timeline: Week 2 of each month.
3. Implement feedback and monitor client satisfaction. | 3. Present tailored upsell proposals and case studies. | 1. Create and post LinkedIn updates.
Success Metric: High client satisfaction score, low churn rate. | Success Metric: Number of proposals presented. | Success Metric: 3 LinkedIn posts per fortnight.
Timeline: Ongoing. | Timeline: Week 3 of each month. | Timeline: Every two weeks.
4. Review progress and adjust strategies as needed. | 4. Follow-up and negotiate upsell deals.
Success Metric: Retained clients and consistent revenue. | Success Metric: Number of upsell deals closed, additional revenue generated. | Milestones by August:
Timeline: Quarterly review. | Timeline: Week 4 of each month.
1. Launch the updated company website.
Success Metric: Website launched and live.
Timeline: By end of August.
2. Develop and publish a dashboard portfolio.
Success Metric: Dashboard portfolio available online.
Timeline: By end of August.
Cross Sell Target Per Quarter
Q2 | 160000
Q3 | 240000
Q4 | 320000

## Timeline
CarbonEye Week on Week OKR
[7 empty] | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37 | WEEK 38 | WEEK 39 | WEEK 40
Phase 1: Establish Foundation and Begin Outreach
| Aim to generate at least 5 SQLs | 2024-06-01 | 2024-06-28 | 27 |  | 100%
| Conduct one meeting per week to review progress with Lead Gen Team |  |  | 0 |  | 80%
| Validate initial email templates and LinkedIn outreach messages. | 2018-01-11 | 2018-01-16 | 4 |  | 60%
| KT To Lead Gen Team for Call Script | 2018-01-14 | 2018-01-19 | 5 |  | 40%
| Support the Launch of Initial Campaigns | 2018-01-17 | 2018-01-21 | 3 |  | 20%
| Help in Content Idea for Landing Page | 2018-01-20 | 2018-01-23 | 2 |  | 10%
Phase 2: Refine and Expand
| Post 3 Linkedin Posts per fortnight showcasing company expertise. | 2018-02-05 | 2018-02-08 | 4 |  | 100%
| Start developing initial case studies and landing pages. | 2018-02-08 | 2018-02-13 | 4 |  | 80%
| Highlight key benefits and success stories through My Linkedin Posts | 2018-02-11 | 2018-02-16 | 5 |  | 60%
| Analyze Results of Email Campagin and Plan action forward | 2018-02-14 | 2018-02-23 | 8 |  | 40%
One potential client meeting conducted
Phase 3 - Identify Opportunities for Cross Sell
| Adjust email and LinkedIn messages based on initial feedback | 2018-03-05 | 2018-03-08 | 4 |  | 100%
| Deploy New Assets: Use case studies and landing pages in campaigns. | 2018-03-08 | 2018-03-13 | 4 |  | 80%
| Client Engagement: Continue personalized outreach | 2018-03-11 | 2018-03-16 | 5 |  | 60%
| Client Meeting: Conduct one meeting per week to review progress | 2018-03-14 | 2018-03-19 | 4 |  | 40%
| Launch Asset-Enhanced Campaigns: Integrate new assets into ongoing campaigns | 2018-03-17 | 2018-03-21 | 3 |  | 20%
| Webinar Preparation: Plan and promote the first webinar | 2018-03-20 | 2018-03-25 | 4 |  | 10%
Phase 4 -Broaden The horizon
| Social Media Push: Increase social media activity with new content | 2018-04-05 | 2018-04-08 | 2 |  | 100%
| PR Outreach: Publish articles and press releases in industry publications | 2018-04-08 | 2018-04-10 | 2 |  | 80%
| Expand Outreach: Target new industries and roles | 2018-04-11 | 2018-04-16 | 4 |  | 60%
| Adjust Strategy: Based on feedback from previous months. | 2018-04-14 | 2018-04-18 | 3 |  | 40%
Phase 5 - Develop Gallery of Dashboard & GitHub Resources
| Develop Industry-Specific Content: Create case studies, whitepapers, and webinars for new segments | 2018-04-05 | 2018-04-08 | 2 |  | 100%
| Launch Expanded Campaigns: Roll out campaigns targeting new industries | 2018-04-08 | 2018-04-10 | 2 |  | 80%
| Event Participation: Attend and sponsor industry events and webinars | 2018-04-11 | 2018-04-16 | 4 |  | 60%
| Adjust Strategy: Based on feedback from previous months. | 2018-04-14 | 2018-04-18 | 3 |  | 40%
Phase 6 - Consolidate and Prepare for Scale
| Consolidate Gains: Review and document successful strategies | 2018-04-05 | 2018-04-08 | 2 |  | 100%
| Prepare for Scale: Set up for larger-scale campaigns | 2018-04-08 | 2018-04-10 | 2 |  | 80%
| Client Meeting: Conduct one meeting per week to review progress | 2018-04-11 | 2018-04-16 | 4 |  | 60%
| Adjust Strategy: Based on feedback from previous months. | 2018-04-14 | 2018-04-18 | 3 |  | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])